## Sheet6
Responsible Team | (All)
Count of Phase / Work Package | Column Labels
Row Labels | 1.0 | 1.1 | 1.2 | 2.0 | 2.1 | 2.2 | 3.0 | 3.1 | 3.2 | 4.0 | 4.1 | 4.2 | 5.0 | 5.1 | 5.2 | 6.0 | 6.1 | Grand Total
Sprint 1 |  | 1 | 1 | [14 empty] | 2
Project Charter and Kick-off |  | 1 | [15 empty] | 1
Scrum Team Setup |  |  | 1 | [14 empty] | 1
Sprint 10 | [13 empty] | 1 |  |  |  | 1
Conduct End-user Training | [13 empty] | 1 |  |  |  | 1
Sprint 11 | [14 empty] | 1 |  |  | 1
Execute Cutover Plan | [14 empty] | 1 |  |  | 1
Sprint 12 | [16 empty] | 1 | 1
Hypercare Support and Stabilization | [16 empty] | 1 | 1
Sprint 2 |  |  |  |  | 1 | [12 empty] | 1
Gap Analysis (VAS vs IFRS) |  |  |  |  | 1 | [12 empty] | 1
Sprint 3 | [5 empty] | 1 | [11 empty] | 1
Design IFRS 1, 15, 16 Policies | [5 empty] | 1 | [11 empty] | 1
Sprint 4-6 | [7 empty] | 1 | [9 empty] | 1
SAP FI/CO Configuration | [7 empty] | 1 | [9 empty] | 1
Sprint 5-6 | [8 empty] | 1 | [8 empty] | 1
Configure Parallel Ledgers | [8 empty] | 1 | [8 empty] | 1
Sprint 7 | [10 empty] | 1 | [6 empty] | 1
Master Data Cleansing | [10 empty] | 1 | [6 empty] | 1
Sprint 8-9 | [11 empty] | 1 | [5 empty] | 1
Perform User Acceptance Testing (UAT) | [11 empty] | 1 | [5 empty] | 1
(blank) | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  | 6
Data Migration & Testing | [9 empty] | 1 | [7 empty] | 1
Gap Analysis & IFRS Policy Design |  |  |  | 1 | [13 empty] | 1
Hypercare & Post-Go-live Optimization | [15 empty] | 1 |  | 1
Project Preparation & Planning | 1 | [16 empty] | 1
SAP Configuration & Development | [6 empty] | 1 | [10 empty] | 1
User Training & Go-live | [12 empty] | 1 |  |  |  |  | 1
Grand Total | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17

## Sheet1
WBS Code | Phase / Work Package | Responsible Team | Estimated Sprint
1.0 | Project Preparation & Planning
1.1 | Project Charter and Kick-off | PMO | Sprint 1
1.2 | Scrum Team Setup | Scrum Master | Sprint 1
2.0 | Gap Analysis & IFRS Policy Design
2.1 | Gap Analysis (VAS vs IFRS) | IFRS Advisors + Finance | Sprint 2
2.2 | Design IFRS 1, 15, 16 Policies | Product Owner | Sprint 3
3.0 | SAP Configuration & Development
3.1 | SAP FI/CO Configuration | SAP Consultants | Sprint 4-6
3.2 | Configure Parallel Ledgers | SAP Consultants + IT | Sprint 5-6
4.0 | Data Migration & Testing
4.1 | Master Data Cleansing | Key Users | Sprint 7
4.2 | Perform User Acceptance Testing (UAT) | QA + Business Users | Sprint 8-9
5.0 | User Training & Go-live
5.1 | Conduct End-user Training | Change Manager | Sprint 10
5.2 | Execute Cutover Plan | PMO + SAP Core Team | Sprint 11
6.0 | Hypercare & Post-Go-live Optimization
6.1 | Hypercare Support and Stabilization | ERP Support Team | Sprint 12
Estimated Sprint
Sprint 1
Estimated Sprint
Sprint 1
Sprint 1
Sprint 2
Sprint 3
Sprint 4-6
Sprint 5-6
Sprint 7
Sprint 8-9
Sprint 10
Sprint 11
Sprint 12